## Instructions
Risk Assessment Tool for Sexual Exploitation, Abuse and Harassment (SEAH)
Date published: July 2022 (Updated March 2023)
The grant-level SEAH risk assessment is expected to be carried out during the country dialogue once the content of the interventions to be proposed for funding is defined; this assessment can also be carried out during grant implementation, in a participative and inclusive setting, including representatives of the key program beneficiaries. If the risk assessment tool is submitted at funding request stage (optional annex for the 2023/2025 Allocation Cycle), during grant making Principal Recipients are expected to provide follow up to any mitigation measure proposed and confirm the relevance of its content, including timelines and implementers. In case submitted as an optional annex, the SEAH Risk assessment is expected to be reviewed and updated annually to make sure that any changes to the program and the mitigation measures are reflected; if an annual udpate is not provided, the Secretariat will assume that the previous version of the risk assessment is still valid.
The following steps are to be completed in the corresponding columns in the Risk Assessment Tool:
Step 1: | In column A, list key beneficiaries linked to the program interventions. Be as detailed as possible:
(e.g., PLWH, MSM, AGYW, TB patients, sex workers, transgender people, indigenous people, AGYW/Refugees, MSM/IDPs, unaccompanied children in refugee camps, etc.).
Step 2: | In column B, list priority interventions targeting beneficiaries and including the provision of goods or services .
Step 3: | In column C, identify risks of SEAH that each stakeholder group may face in the context of program activities.
Step 4: | In column D, describe the measures already in place to mitigate risk of SEAH.
Step 5: | In column E, assess the likelihood of the risk occurring, and in column F assess the severity of the impact if the risk were to occur (while considering the mitigation measures already in place). The risk of harm will be automatically calculated in column G.
For each risk identified per stakeholder group, assess the likelihood and severity of the risk occurring, using the considerations below:
Likelihood - How likely is the risk to occur?
50 to 75% chance that the risk event will occur in the next 12 months (highly likely)
25 to 50% chance that risk event will occur in the next 12 months (likely)
Less than 25% chance that the risk event will occur in the next 12 months (unlikely)
Severity - how severe the impact might be in terms of the victims/survivors and of the program to be able to achieve expected results (please consider potential impact in terms of loss of life, unwanted pregnancies, physical injury and/or nonphysical threats and harm to members of the population, including victims, witnesses and children born as a result of SEA, psychological treaths and harm, loss of job, stigma etc..)
Major
Moderate
Minor
Risk Rating
Impact
Likelihood |  | Likelihood | Minor | Moderate | Major
Highly Likely |  | Highly Likely | Medium | High | High
Likely |  | Likely | Low | Medium | High
Unlikely |  | Unlikely | Low | Medium | Medium
Step 6: Mitigate | In column H, define additional risk mitigation measures/actions for risks identified per stakeholder. In columns I and J, define and assign entities responsible and accountable for implementation of the mitigation measures and the expected timeline for their implementation.
Please note that grant funds cannot be used to fund mitigation measures aimed at PSEAH capacity building for implementers / service providers; in cases where no other sources of funding are available, PRs can ask for additional resources through the submission of a capacity building plan. For more information on this subject please read the Guidance Note on PSEAH or write to PCU@theglobalfund.org
Step 7: Mitigate - Community awareness activities | In column K, propose mitigation measures related to SEAH community awareness activities targeting beneficiaries. In columns L and M, define and assign entities responsible and accountable for implementation of the mitigation measures and the expected timeline for their implementation
Step 8: | In column N, the CCM is expected to sign off on the risk assessment confirming that the process has been participative and inclusive and that will provide oversight over the implementation of the mitigation measures; the PR is responsible for implementing the mitigation measures.
Step 9: | In column O 'comments', please include information on the process carried out to complete the risk assessment, describing the groups and stakeholders participating in the identification of the SEAH related risks and mitigation measures.
Step 10: | Complete the 'additional_information' tab with contextual information

## risk_assessment_tool (hidden)
GRANT LEVEL SEXUAL EXPLOITATION, ABUSE AND HARASSMENT (SEAH) RISK ASSESSMENT AND MITIGATION TOOL - EXAMPLE
GRANT : FCT-M-YOU
Date of initial risk assessment and regular updates of the assessment – 23.2.2023, annual updates
Date of update
| PSEAH contextual information (if any), including details on what partners are doing | Eg: UNICEF is part of the CCM and has a referral network for victim support
Intervention - please only list the interventions including the provision of good or services | Beneficiairies | Describe the risks per intervention and by beneficiary group | Risk of harm Low Medium High | Risk Mitigation Actions/measures | Entity in charge for the mitigation measure to be in place | Expected timeline for the measure to be in place (please clarify whether it is already in place) | SEAH community awareness activities aimed at beneficiaries – please state what | Entity in charge for the mitigation measure to be in place | Expected timeline for the measure to be in place (please clarify whether it is already in place) | Comments | signed off by:
Risk Assessment Examples
LLINs distribution | indigenous people | Women and children alone at home during LLIN distribution may be at risk of SEAH by service providers | high | Ensure distribution groups/teams are composed of women and men, of at least 3 people | PR, by start of service provision |  | Targeted malaria prevention campaign including awareness of SEAH and reporting channels | Sub recipient n. 2, by Q5 |  | n/a
|  | Women and children alone at home during LLIN distribution may be at risk of SEAH by service providers | high | Ensure that service provider staff is aware of the Code of Conduct and has been trained on SEAH | SR n. 2, by Q3 |  | n/a | n/a |  | n/a
Intervention: RSSH – lab systems - Information systems and integrated specimen transport networks
| Lab system and staff | Lab staff receiving TA and training might be at risk of SEAH by service providers | Low | no mitigation measures are planned | n/a |  | n/a | n/a
Intervention -HIV prevention - behavioural change program
| MSM | MSM participating in events or training might be at risk of SEAH by service providers | Medium | Ensure service provider staff is aware of code of conduct and has knowledge of PSEAH | PR, by Q1 |  | Communication material and training on SEAH and reporting mechanism | SR n.2, by Q2
Intervention: RSSH-CSS- Institutional capacity building, planning and leadership development
| People Living with HIV | PLWH might be at risk of SEAH to get access to training or other benefits designed to strengthen their capacities and abilities | high | Approval of training participation subject to the review by a committee | SR n.2, by the starting of the grant |  | Communication material and training on SEAH and reporting mechanism | PR, by Q3

## Risk Assessment Tool
Risk Assessment Tool for Sexual Exploitation, Abuse and Harassment (SEAH)
| Instructions: | Examples are in grey |  |  |  | Please fill all blue cells
Country and components |  | Ficticia, Malaria , HIV
GRANT(S) name(s) (if available) |  | FCT-M-YOU, FCT-H-VIV
Grants starting date |  | 01.01.2022
Date of initial risk assessment |  | 23.02.2021 for M and 20.02.2021 for HIV
Date of review during grant making, if any |  | 23.11.2021 for M and 25.11.2021 for HIV
Date of last update |  | 23.11.2021 for M and 25.11.2021 for HIV
PSEAH contextual information (if any), including relevant circumstances in the country (e.g. humanitarian context) that could cause additional vulnerabilities to SEAH; strengths or weaknesses in local social and child protection systems; existence or absence of local victim/survivor support services; and details on what partners are doing in relation to PSEAH |  | Eg: UNICEF is part of the CCM and has a referral network for victim support to the existing local public and private resources E.g. The recent floods have caused an unprecedented humanitarian crisis and the migration of internally displaced persons (IDPs) into the program areas. The need for rapidly recruiting more community workers may lead to implementers taking short cuts in recruitment without background checks or without trainng them on PSEAH.
Beneficiaries Please describe the beneficiaries of your program e.g., PLWH, MSM, AGYW, TB patients, sex workers, transgender people, indigenous people, Internally Displaced Persons (IDPs), refugees, etc. | Interventions Please list priority interventions targeting beneficiaries and including the provision of goods or services | Describe the risks per intervention and by beneficiary group | Describe the mitigation measures already in place | Likelihood of risk occurring | Impact if risk occurs | Risk of Harm (likelihood plus impact) Low Medium High | Additional Risk Mitigation actions/measures | Entity in charge for the mitigation measure | Expected timeline for the measure to be in place | SEAH community awareness activities aimed at beneficiaries – please state what | Entity in charge for the mitigation measure to be in place | Expected timeline for the measure to be in place | Signed off by CCM is expected to sign off and provide oversight over the implementation of the mitigation measures, while the PR is responsible for implementing them. | Comments Please include information on the process carried out to complete the risk assessment, describing the groups and stakeholders participating in the identification of the SEAH related risks and mitigation measures.
Internally Displaced Persons (IDPs) | Insecticide Treated Nets (ITNs) distribution | Women and children are particularly vulnerable due to their status as IDPs. If women and/or children are alone at home during ITNs distribution they may be at risk of SEAH by service providers | N/A | Likely | Major | High | Ensure distribution groups/teams are composed of women and men, of at least 2-3 people | PR M | By start of service provision | Targeted malaria prevention campaign including awareness of SEAH and reporting channels | SR M n.1 | Q1, 2023 | CCM chair, vice chair or nominated representative | representatives of IDP participated to the conultation process
|  |  |  | Likely | Major | High | Ensure that service provider staff working with IDPs are aware of the Code of Conduct and has been trained on SEAH | PR M | As part of induction training
Children and adolescents | TB/DR and TB - KVP - Children and adolescents | Children and adolescents may be at risk of SEA from service providers (health personnel/community workers) during testing and treatment | N/A | Likely | Major | High | Ensure that children and adolescents are always accompanied by a parent/guardian during testing, screening and treatment | SR TB n. 2 | Q3, 2022 | Age appropriate awareness raising campaign on SEAH for children and adolescents who are beneficiaries and for their parents/guardians | SR TB n3 | Q4, 2022 | CCM chair, vice chair or nominated representative | representatives of TB patients participated to the consultation process
|  |  |  | Likely | Major | High | Ensure that service provider staff working with chiildren and adolescents have been vetted when recruited and are aware of the Code of Conduct and have been trained on SEAH | SR TB n. 2 | As part of recruitment and induction
MSM | HIV prevention -communication: information and demand creation for MSM - behavioural change program | MSM participating in events or training might be at risk of SEAH by service providers | Service provider staff is aware of code of conduct and has knowledge on PSEAH | Unlikely | Moderate | Medium |  | PR HIV | Q1, 2022 | Communication material and training on SEAH and reporting mechanism | SR HIV n.2 | Q2, 2022 | CCM chair, vice chair or nominated representative | MSM representatives participated to the consultation process
PLWH | RSSH-CSS- Institutional capacity building, planning and leadership development | PLWH might be at risk of SEAH to get access to training or other benefits designed to strengthen their capacities and abilities | N/A | Likely | Major | High | Approval of training participation subject to the review by a committee | SR HIV n.2 | Q1, 2022 | Communication material and training on SEAH and reporting mechanism | PR HIV | Q3, 2022 | CCM chair, vice chair or nominated representative | PLWH representatives participated to the consultation process
AGYW in high HIV incidence settings | Social Protection interventions | AGYW might be at risk of SEAH to get access to cash transfer programs created to foster school attendance | There is a clear process in place to allocate the benefit | Likely | Major | High | The decision is made by a committee and the cash is distributed at school during the lesson | SR HIV n.4 | Q2, 2022 | Communication material and training on SEAH and reporting mechanism for all beneficiaries in the program | PRn.2 HIV | Q3, 2022 | CCM chair, vice chair or nominated representative | AGYW representatives participated to the consultation process
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact
Please select Likelihood & Impact

## Additional_information
Risk Assessment Tool for Sexual Exploitation, Abuse and Harassment (SEAH)
| Instructions: | Examples are in grey | Please fill all blue cells
FCT-M-YOU, FCT-H-VIV
Country and components |  | Ficticia, Malaria , HIV
GRANT name (if available) |  | FCT-M-YOU, FCT-H-VIV
Grant(s) starting date |  | 01.01.2022
Date of initial risk assessment |  | 23.02.2021 for M and 20.02.2021 for HIV
Date of review during grant making, if any |  | 23.11.2021 para M y 25.11.2021 para VIH
Date of last update |  | 23.11.2021 para M y 25.11.2021 para VIH
Please describe the process carried out to fill in the risk assessment tool |  | The CCM organized the consultations with the civil society to provide endorsement on the proposed interventions for the new funding request. Representatives of key populations, vulnerable communities and people affected by the diseases participated to the process. The group was divided in 4 groups with an heterogenous composition, and each group was requested to provide inputs on the different interventions. Then a representative of each group informed the plenary of the comments provided. All the participants unanimously voted for the preferred scenarios in terms of risk and mitigation measures, and then the checklist was filled in.
Please describe the challenges faced during this process |  | It was difficult to set up the methodology and identify the people who could facilitate this process.
Please describe the lessons learned |  | Communities and key populations are aware of the risks and have ideas about possible solutions.
Please confirm whether community reporting systems are in place |  | Beneficiaries have several channels to report SEAH confidentially, including community reporting mechanisms/focal points or directly to the SR or PR. Beneficiaries can report in writing or verbally (independent of literacy levels) and in their local language.
Areas of improvements and suggestions for the Global Fund Secretariat
Other comments

## To be hidden (hidden)
Low
Medium
High