## C19RM Assurance Approach
C19RM Assurance Guidelines | 2024-03-19
General principles of assurance approach for C19RM
Assurance activities should be: • proportionate to the nature of investments, level of risk involved, and value of information obtained compared to the cost incurred in obtaining the assurance. • tailored to the country context and needs considering the grant budget drivers, type of implementer and risk profile; and • the most effective given the context, lessons learnt, best practices and within the Global Fund’s span of control and/or influence. All portfolios shall plan and implement as per the regular practice, risk-based, investment-driven LFA assurance activities across the updated C19RM investment priorities: i. Risk based: e.g., procurement / asset management / fraud and fiduciary / programmatic / implementation risks; and ii. Investment-driven: the C19RM Additional Funds and/or reinvestments of US$ 5 million or more approved towards strategic priorities. In addition, the following minimum assurances for High Impact/Core portfolios apply: i. for high-risk contexts (high/very high procurement and fraud risks): pre-award procurement reviews for in-country procurement of strategic and mainstream health products. ii. as relevant (based on C19RM investment areas) in 2023 – 2025: assurance for PSA plants, waste management, and laboratory equipment. iii. at least in 2023: supply chain reviews to review stock levels and expiries of health products used to implement C19RM activities (e.g., diagnostics/therapeutics) irrespective of source of funding. LFAs are the primary provider of downstream assurance services. Global Fund also leverages and uses partner data and reports where available, more specifically on COVID-19 burden and delivery of services. First Line (Country Teams) and Second Line functions may also decide to engage alternative providers who may be better positioned to provide specific assurance services. C19RM assurance leverages services planned for HIV, TB and malaria and should be adapted to incorporate C19RM as appropriate. In most cases this will involve changes in the scope and Level of Effort (LOE) of LFA assurance activities already planned. For non-LFA led assurance, this may also require that terms of reference (ToRs) are adapted to include oversight on C19RM interventions (e.g., Audit Terms of Reference). Assurance planning is an ongoing process which all portfolios (High Impact/Core/Focused) initiate at C19RM Additional Funding Request review stage to mitigate incremental risks identified based on planned implementation arrangements, capacity of implementers and systems (procurement capacity, knowledge of risks related to supply chain systems; mechanisms to process the funds, e.g., cash payments, etc.), investments priorities and program design. These recommendations are captured under the cross-functional Secretariat reviews in the C19RM Review and Recommendation Form (RRF) and may be communicated to the country as requirements in the C19RM Notification Letters following the C19RM Investment Committee (or Board) decision. (Refer to Part 4 Section 1 of the C19RM Guidelines). C19RM-related risks, mitigations and assurance plans must be captured in the Integrated Risk Management Module (IRM) for High Impact and Core Portfolios and updated during the course of grant implementation. The Pulse Checks collect information on the extent of grant, programmatic and service delivery disruptions, key financial and supply chain performance indicators and select indicators to monitor delivery of HIV, TB and malaria services.

## C19RM Assurance Service Menu
Menu of C19RM assurance service |  | 2024-03-19
Assurance area | Investment and/or Risk areas | Assurance Provider | ToR 1 (if available) | ToR 2 (if available) | Focus of assurance
HPM/SC | Medical oxygen, respiratory care and therapeutics | LFA | Review of implementation of PSA oxygen generating plants |  | 1. Review of end-to-end implementation of PSA (pressure swing absorption) oxygen generating plants, incl: 2. Availability of oxygen and /or oxygen delivery equipment and warranty, maintenance, piping or technical assistance
HPM/SC | Laboratory systems and equipment | LFA | Joint Programmatic/M&E, Laboratory Investments and related Supply Chain review |  | 1. National diagnostic governance: Coordinated lab activities at national and district level 2. COVID-19 testing and surveillance, including sufficient and trained staff to ensure full testing coverage. 3. Data management including Laboratory Information Management System (LIMS) 4. Functional and integrated sample transportations 5. Availability of functional lab equipment/commodities/consumables, including equipment has a current service contract, undergoes routine maintenance (including calibration) and that there is evidence of this (contract at central or peripheral level and existence of an upto-date log book for each equipment 6. Efficient deployment and use of equipment/reagents 7. Quality and consistency of lab services delivery. incl. lab test results 8. Biosafety & biosecurity including environmental risks.
Programmatic | Human resources for Health and Community System | LFA | Review of Human Resources of Health ToR forthcoming |  | 1. Verification that Management / Strategic Actions on HRH/CHWs have been met 2. Availability of sufficient and trained health staff / conduct or verify HRH/CHW inventories 3. Capacity assessment in HRH/Community health Departments 4. Adequate training on pandemic preparedness and response 5. Effectiveness and efficiency of community outreach services, including identification of integration opportunities 6. Coordination/streamlining of different approaches for community led monitoring and community surveillance 7.Clearly defined the roles/responsibility of each actor at community level 8. Review CHW system maturity components (e.g. integrated service package, remuneration level comparison, legal status of CHWs) / verify CHW system maturity scores
Programmatic | Surveillance System | LFA | Review of Surevillance Systems to be integrated in Implementer Capacity Assessment - forthcoming |  | Impementation monitoring: 1. At the beginning of the grant period, provide a written assessment of the public health directorates/surveillance department's readiness to launch implementation (do they have detailed workplans, assigned program staff, clear understanding of TGF requirements to access funds and aware of how much funds are allocated etc.) 2. After implementation begins, every quarter provide a report on implementation status
HPM/SC | Local procurement of health products/equipment | LFA | Local Fund Agent Procurement Review Tool |  | 1. Adequate procurement processes, tendering procedures and contract awards, including compliance to procurement regulatuions/planning/procedures/guidelines. 2. Value of money of the procurement
HPM/SC | LMIS investments | LFA | LMIS Implementation Review |  | 1. Availability of integrated data collection and reporting tools 2. Adequate data quality control mechanisms 3. Appropriate data used for management and service delivery 4. Adequate human resources capacity for LMIS daa capture and reporting 5. Adequate infrastructure for LMIS, incl. back up/security/maintenance systems 6. Data management and repository 7. Synergies/links between LMIS and other systems
HPM/SC | Warehousing/Inventory management/Expiries | LFA | Verification of Health Product Expiries Guidance Note | Supply Chain Management Review | 1. Adequate controls for receiving of goods, stock placement and location, inventory control and records management, order processing, inventory counts, order release and dispatch, good house-keeping, equipment management, etc 2. Status of expiries (over past 12 months) and products at risk of experiry in coming 6 months 3. Goods are received, stored, and managed in accordance with Good Storage Practices 4. Effective systems and controls to minimize the risk of stock-outs, over-stocks and expiry
HPM/SC | Distribution | LFA | Supply Chain Management Review |  | 1. Distribution in accordance with Good Distribution Practices 2. Goods are distributed according to plan (quantity, type of products, quality, frequency of receipt, at no charge for beneficiaries 3. Reconciliation of quantities ordered, received at central level, dispatched and received at site
HPM/SC | Waste Management | LFA | Health Care Waste Management Assessment ToR | Health Care Waste Management Assessment Tool | 1. Waste management plans are aligned with national, subnational, or local strategies, and governmental authorities are engaged. 2. Waste management technologies/equipment are functional, appropriate for the healthcare context, and in-line with global standards. 3. Appropriate waste management policies and procedures (collection, storage, transportation, treatment, disposal) for used, expired or damaged health products (e.g., PPE, cartridges etc.) and biomedical samples are in place, including adherence to occupational health and safety standards for waste handlers
HPM/SC | Quality assurance of health products | LFA | 1. QA verification of ERPD risk mitigations 2. QA verification of pharma registration for nATM FPP 3. QA verification of product recall procedures |  | 1. Adequate Quality Assurance planis in place and quality monitoring activities are implemented, including Quality Control testing for health products at country level as required under the Global Fund Quality Assurance Policies. 2. Products procured (as reflected on the invoice e.g., INN, batch number, manufacturer) are the products received (availability of a valid Certificate of Analysis (CoA), where applicable).
HPM/SC | Health product quantification | LFA | Health Product Management Template User Guidelines |  | 1. Review of HPMT, e.g. re-programming - as required and when needed 2. Review of quantification before large-scale orders of PPEs, diagnostics, lab equipment and supplies are placed in order to avoid an over- or undersupply of the respective products. 3. Quantification was validated and coordinated among national authorities and partners supplying the same commodities before orders are placed. This review may be requested irrespective of the procurement channel
Programmatic | C 19RM awards with Performance Framework and investment over US$ 20 million | LFA | C19RM Indicator verification spot check ToR forthcoming |  | 1. Onsite verification of reported results to verify data quality, identify implementation bottlenecks and inform quality improvements (up to 20 sites based on volume of results/risks) 2. Systems/mechanisms for reporting from operational to national level 3. Compliance to measurement guidance provided in the Indicator Guidance Sheet - verification of actual vs. reported results
Programmatic | C19RM awards with significant investments in community based activities ands awards over US$ 20 million | LFA | Community Led Monitoring (CLM) |  | 1. Verify whether CLM is being implemented and feedback loops established between health service providers and communities. 2. Systems in place to collect data from clients accessing health services routinely (monthly or quarterly at least) 3. Do communities have access to forums and committees to share data from CLM findings and issues identified for resolution? 4. Are there mechanisms in place to track service improvements once duty bearers and health service providers have been engaged on AAAQ issues and how often does this happen?
Programmatic | Infection Prevention and Control (including PPE) | LFA/Partners | Review of Infection Prevention and Control (IPC) and Pandemic Preparedness |  | 1. IPC authorities at national, subnational, or facility level are actively engaged in planning and implementation. 2. Stock-outs of PPE are not occurring at facility level. 3. IPC policies and guidelines are present in facilities and all health workers have received training on them in the past year
Cross-cutting | Implementation readiness/effectiveness | LFA | Implementationn Readiness Assessment |  | 1. PR has the critical tools and structures in place to allow for timely implementation and adequate absorption, including: a. all required human resources are in place; b. contracts with all SRs are signed; c. contracts with critical suppliers of health products are signed; and d. an agreed implementation work plan for year one of the implementation is available
Cross-cutting | 1. New implementer/changes in risk profile of implementer 2. Scale up/expansion in coverage/service deliery | LFA | Implementer Capacity Assessment |  | 1. Tailored assessment of implementers' controls, systems and capacities in areas considered high risk/low capacity
Financial | Accounting and financial reporting | LFA | PUDR |  | 1. verification of PR reported expenditures for C19RM funds against approved budget lines/activities and to source documents (checking invoices and other supporting documents)
Financial | Value for Money – Financial Management | LFA | Budget review |  | 1. review of the C19RM grant budget for relevance of proposed activities, reasonableness of budgeting assumptions used as well as identification on cost efficiencies
Financial | Accounting and financial reporting | LFA | Budget variance analysis |  | 1. review actual financial performance against grant budget 2. identify causes for low absorption
Financial | Financial fraud, corruption, and theft | LFA | Expenditure Verification/ Fraud specific reviews |  | 1. Expenditures verification to ensure C19RM expenditures are comliant with terms and conditions of the grant confirmation, the agreed grant budget and GF policies 2. Suspicions of instances of misappropriation or fraudulent use of funds
Financial | Accounting and financial reporting | External auditor | Annual Financial Audit |  | 1. Obtain reasonable assurance that financial statements are prepared in accordance with an applicable financial reporting framework. 2. The scope of the annual financial audits and the audit opinion will cover both, core HIV, TB and malaria funding and C19RM Funds, including internal control findings in the management letter.
Financial | Financial fraud, corruption, and theft | LFA | Finance Implementation Verifications and Spot-Checks |  | 1. Financial verifications done at high-risk implementers/high-risk activities/interventions susceptible to misuse whether due to fraud or misappropriation
Financial | Asset management | LFA | Fixed (non-health) Assets Verification |  | 1. C19RM assets are adequately managed and accounted for
Financial | Flow of funds arrangement | LFA | Review of Funds Flow Adequacy |  | 1. The funds reach their intended recipients, i.e. implementers and/or beneficiaries of the program activities, in acceptable time; 2. Funds transfer mechanisms used by the implementers are effective and secure; 3. Cash management procedures are adequate to release funds timely and accurately;
Financial | Accounting and financial reporting | LFA | Financial Data Quality Review |  | 1. Completeness, accuracy, and reasonableness of cash/stock/assets reconciliation, expenditure forecast, and cash flow forecast in relation to C19RM funding.
Financial | Internal controls | LFA | Review of Effectiveness of Internal Control Environment |  | 1. Controls are designed and operating effectively, 2. Global Fund resources are not lost as a result of lack of (i) well designed and effective control at entity; (ii) compliance with policies, procedures and applicable law; and (iii) safeguarding of assets.
Financial | C19RM Grant Closure | LFA | Review of Fin. Closure Rpt. (FCR)/Carry Forward cash balances |  | 1. Review of FCR submitted by the PR
8

## Principles_Assurance Delivery
Principles of C19RM Assurance service delivery |  |  | 2024-03-19
Timing of COVID-19 Related Assurance | Methods of Assurance | Assurance Service Delivery |  | Output/Deliverables | Information Sharing | Management Of C19RM Assurance Activities in the LFA Work Plans
1. Preference for ex ante versus post factum verifications as much as possible, real-time as opposed to post-factum verifications to obtain: - early alerts to issues is to allow the Country Team to take timely rectifying actions - insights into potential bottlenecks, delays or risks as the PR plans and starts to implement interventions. For example: review of distribution plans before they are being implemented and physical verifications of distributions of PPEs/diagnostics, laboratory equipment or other products to health facilities. | 1. Preferably, physical verifications on a sample basis, such as site visits to health facilities to verify the storage and management of health products (diagnostics, therapeutics and oxygen), usage of laboratory equipment; interviews with health care providers to check their satisfaction with the supply of such products and availability of products, etc. 2. Prior to the start of the verification, Global Fund Country Team and LFA agree on the geographic areas to be covered and the sampling methodology (how many sites and locations; sample size of health care providers to be interviewed; period of time being reviewed; etc.). Note: Due to certain travel restrictions in some countries, physical verifications may not always be possible. In such cases, the LFAs should agree with their Global Fund Country Teams alternative verification methods, for example, telephone interviews with health care providers | 1. LFAs are the primary provider of assurance services. In addition, the Secretariat and/or Country Teams may use other potential providers to provide some specific assurance services. 2. The circumstances should be specifically assessed to determine the best and most cost-effective method of obtaining assurance over the funds, if at high risk and material, such as relying on the national auditor, external auditors, donor auditors or other measures. 3. All assurance tasks should be led by experts with the the approriate technical expertise. For exmpales; HPM/SC related assurance should be led by a PSM Expert; finance related assurance activities should be led by a Finance Professional and programatic services by Programmatic/M&E experts who are accountable for the technical content of the reports. S/he can be supported, as needed, by other assurance team members in the planning and during the verification, especially if the experts cannot travel to the country. 4. It is key that the various assurance team experts (e.g., PSM, Lab, Finance and Programmatic/M&E experts) consult each other to ensure appropriate linkages and analysis. 5. The level of effort (LoE) of the services, including for report writing, depends on the scope of the assurance tasks and the number and location of service delivery sites included in the review, and should be agreed in writing between the Country Team and the assurance provider prior to the start of the service. |  | 1. For assurance services where the Global Fund has a specific template for reporting findings and recommendations (e.g., PUDR), thew assurance provider should continue using these templates. In other cases, it should prepare a report that addresses each of the points selected for review as agreed between the Country Team and the assurance provider and be supplemented with other relevant information, as appropriate. The report should include without limitation: a) A description and analysis of issues/risks identified. The assurance provider should comment on the context and potential root causes of the issues identified, providing background information as necessary and prioritize the list of issues according to their significance. b) Recommendations for addressing issues identified. Recommendations should be: • Concise but with all the relevant information included. • Specific and contextualized. • Time-bound. • Prioritized based on the level of risk; and • Identifying the main entity responsible for implementation. The main findings from the review/verification should be discussed with the PR/implementer during a de-brief meeting. Relevant observations from the de-brief should be included in the final report to the County Team. 2. After the LFA has provided a C19RM assurance service and submitted a detailed report together with an executive summary to the Country Team, the LFA is requested to replicate the final version of the executive summary in an online survey tool. This requirement is applicable for all C19RM LFA services which have a minimum total LoE of 2 days with the exception of the following services, which do not require an executive summary submission: • COVID-19 Additional Funding Request-related (e.g., review of C19RM Grant Budget, Health Product Management tool) Note: executive summary for implementer capacity assessment (CAT) is required. • Grant-making, review of reprogramming; review of extensions. • Budget review. • PU/PUDR. • Financial Closure Report. • CCM/Partner related (meetings, etc.). • Global Fund country visits (FPM/CT); and • Others, such as ongoing monitoring, meeting attendance, calls etc., where no specific report is prepared by the LFA for the Global Fund. Note: differentiated requirements for submitting the detailed LFA report to the Country Team: • High Impact, Core portfolios: the LFA must submit the detailed report and the executive summary to the Country Team prior to submitting the final executive summary online. • Focused portfolios: the LFA must submit the executive summary to the Country Team prior to submitting it online; the detailed report should be submitted to the Country Team if it was agreed between the Country Team and the LFA that a detailed report will be required. | 1. As per the normal practice and the provisions in the LFA Communication Protocol, the LFA reports are confidential and for internal Global Fund use only. 2. However, there may be occasions when the Global Fund may choose to disseminate some aggregate (rather than country-specific) data with external parties. Disclosure of country-level information which could be linked to a specific LFA is not in principle allowed without prior written LFA consent and must be coordinated with the LFA Coordination team. | Only LFA assurance activities directly related to C19RM should be recorded in the dedicated LFA C19RM work plan. This is to ensure that spending for COVID-19 related assurance activities can be accurately tracked and reported.
1. LFA services related to C19RM are recorded and managed in separate dedicated LFA work plans and purchase orders marked as “C19RM”. 2. The dedicated LFA C19RM work plans and purchase orders for C19RM related LFA services allow for clear ringfencing, traceability & reporting of the LFA C19RM budget, as required by the Global Fund Board. 3. In these dedicated LFA C19RM work plans, the CTs/LFAs should use regular LFA service names that best describe the nature of the service. For example, if the LFA will conduct a procurement review in relation to C19RM funding, they should record this service under “Procurement Transactions/Tender Review” in the LFA C19RM work plan. 4. In cases where C19RM-related verifications are embedded in planned services related to HIV, TB and Malaria grant activities, the LFA LoE should be split between the regular LFA work plan and the LFA C19RM work plan as much as possible. For example, if a planned spot check was expanded to include a C19RM component, the service should be split into two parts with the part relating to the C19RM component being recorded in the LFA C19RM work plan and the part relating to HIV, TB and Malaria grants being recorded in the regular LFA work plan. The exception is the PU/PUDR review with respect to C19RM, which should be recorded as one service “PU (without DR)” or “PUDR” in the regular LFA work plan. The same applies to LFA reviews of Financial Closure Reports (FCRs) which may include C19RM expenditures. The FCRs should be recorded in their entirety in the regular LFA work plans.