## General Instructions
SCHEDULE B3 : DEVELOPMENT ROAD MAP
1. GENERAL INSTRUCTIONS
All the instructions for completing this Schedule are contained on this page which should be read in conjunction with the specific instructions relating to Schedule B3 in the main tender document.
This workbook comprises this instruction page, a worked example of a completed objective which is on two pages, 2 blank templates (1 for background and 1 for timelines) and one page for you to input other ideas if you so wish. As stated we recommend you develop between 5 and 10 objectives and add other concepts on the ideas page.
The template itself divides into two worksheets . Page 1 contains a series of questions to provide background and context to the objective and how the project to deliver it will be structured and on Page 2 a project management template has been provided. Please note that as stated in the main tender document you may complete the questions in word and/or use an alternative project management template.
To create templates for further objectives please right click on the tab at the bottom of the page and select move or copy, then select copy. A duplicate of the page is created. We recommend you always work with one blank template available!!
When completing the questions please be brief and to the point and feel free to use bulleted points and if you feel appropriate include (in a word document) diagrams etc. the cells on the background page will auto expand to display what you write
Note: the Worked Example provided is deliberately generic. We would expect you to be more specifc and where possible more granular in your submission
Page 1 Background Information
Supplier Name: Self evident
Objective Name: Please choose a short, self explanatory title for your objective.
Initial Target: The initial target is the value that you hope to create from this objective. Wherever possible it should be expressed in numeric terms but does not necessarily need to be financial terms See the main tender document for an example.
Target Date: This is the date when you anticipate that the value will be realised (which effectively means the end of the project and should therefore correspond to the timeline below). We do not expect precision at this stage and for projects due to complete in 2015 a target month is sufficient and for 2016 a target quarter.
Benefit Sharing Proposal: One of the aims of a strategic partnership is to support both parties meeting their objectives and where value is created to share it between them. This is difficult to do where the value is non financial so we would encourage at least 1-2 of your objectives to have a cost or financial element. Where applicable we would request that you propose how the value created would be shared between you and the Global Fund. This may be a simple 50:50, 60:40 or something more complex and where you feel benefit sharing is not applicable please just enter N/A.
Please note that owing to its funding arrangements the Global Fud is unable to provide large scale investment to its suppliers and therefore projects requiring this will not be considered
Note: Certain answers relating to sponsorship, resources and the governance model may be common across all objectives. If you want to take this approach please provide the details in Objective 1 and then state 'As for objective 1' in the appropriate section in the other objectives.
Note: All the answer spaces in this section will expand to show your text
Initial Objective and Summarised Approach: In this section please define the overall objective and the key elements of the approach being undertaken. See the worked example for the amount of detail required.
Product Set Impacted: This section defines the scope of the project to meet your objectives. Some objectives and their related projects might apply to specific products or groups of products and some might apply to all products. Please enter you view on which products will be impacted or simply enter 'all'.
How Success (Value) is measured. It is important that both parties have an unambiguous, agreed method of measuring value and hence success. This could be simple such as 'USD saved in cost of manufacture' or something more complex. Wherever possible we would encourage simplicity!
Supplier Sponsorship and Resources Required: Successful projects require support and encouragement from a named senior executive within the organisation. This is the sponsor and we ask you to identify them by name or title. Work also requires individuals to undertake it and we request that you identify the level of resourcing required to complete the project. This could be in the form of 2*FTE (Full time Equivalents) for 3 months or, if you prefer, another format.
Actions Needed From the Global Fund: What role does the Global Fund need to play in this project and when?
Actions needed from Other Agencies: Will other agencies need to be engaged and involved in the project, if so , which agencies, what is the requirement from them and when is it required?
Governance Model: This section defines how the project will be managed. Please include your proposals for the following: Regular reporting, Steering Committee. Project Manager and team structure, Periodicity of meetings.
Identified Risks: Please note the top 5 risks to success, Mitigating actions are not required at this stage but please be prepared to discuss this at the workshop
Additional Information Not Covered Above: Please use this space to expand on any point or to provide any additional information you require
Page 2 Timeline
To deliver the objective it is necessary to put together a project plan to ensure that the key activities are understood and that during the project's duration everyone knows the current status and is able to take action to manage effectively and address issues as they arise. The template in Section 3 forms the initial planning document in the form of a Gantt chart.
To complete this section it is necessary to breakdown the project into a series of activities and for each activity to estimate its duration and the key milestones (important stage points) along the way.
At this stage this is only required at relatively high level so the maximum number of activities for each project is limited to 10. Later as we get into detailed planning this number may increase.
How to complete the template.
1. Decide the key activities required to deliver the objective. Some will be dependent on others being achieved and some will run concurrently. Then estimate the duration in weeks for each activity
2. Enter the activity name in the appropriate space in Column D. If you want to add more lines please do so.
3. Estimate the number of weeks the activity will take and then insert this in Column E.
4. We then represent the activity on the timeline as a coloured bar whose length is the same as the the estimated number of weeks. (the colour if the bar is unimportant!)
5. Certain activities cannot commence until others have finished so these are inserted at the correct date.
6. As the plan progresses certain key events will take place, these are the milestones. Insert the number of the milestone in the column of the week you plan it should happen in the row of the specific actitivity to which it applies.
7. In the section starting at Row 40 Enter the number of your milestone in the appropriate quarter and explain what it is.
Note: These are the minimum requirments, additional notes, text boxes etc are welcome if you feel this will enahnce our understanding of your proposal.
Ideas Page
On this page we simply ask you to record you ideas for further value creation either because you do not have enough information to make them an objective, you have run out of objectives or you feel they are something that should be addressed at a later date.
Submission of ideas is NOT manadatory and this response will not be evalauted for completeness.

## Worked Example Background
WORKED EXAMPLE
Schedule B3 Development Road Map |  |  | This worked example is based on a supplier whose objective is to reduce their lead time by changing their manufacturing process. All the activities and products are fictitious and the example is provided only to show how to fill in the template
Page 1 Background Information
Supplier Name | ABC Pharmaceuticals | Initial Target | Lead time reduction from 6 months to 3 months at Plant 23 Stamford
Objective Name | Lead Time Reduction Project | Target Date | 2015-09-01
Benefit Sharing Proposal | All lead time to the Global Fund, any additional financial benefits to be shared 50:50
| Initial Objective and Summarised Approach | Product Set Impacted | How Success(Value) is Measured | There is nothing this side of the line
| Objective is to reduce lead time by the targeted amount through mapping of current supply chain and manufacturing processes followed by a joint option analysis and thereafter implementation of new ways of working with both suppliers and The Global Fund | Fanafavir-Allatrope-Disloxyn All formulations | Value is measured from date of order receipt at Stamford to date product is available for shipping
| Supplier Sponsorship and Resources Required | Actions Needed from the Global Fund | Actions Needed from Other Agencies
| Project will be jointly sponsored by Director, International Programs and the Site Director Stamford. Estimated resources are 3 FTE, 1 100% for co-ordination and 1 25% for data analysis. 20% of PM (see below) | Review and comment on data analysis findings., Attendance at project kick off, option review workshop. Potential investigation and implementation of internal process changes. | PSA: Implementation of changes as directed by the Global Fund. independent PRs to be advised of changes and any benefits from new way of working.
| Governance Model | Identified Risks | Additional Information Not Covered Above
| This project will be managed as part of a portfolio alongside the other projects proposed. We will appoint 1PM for all projects. Suggest a monthly update and call and quarterly formal steering committee alternating VC and F2F. From our side Steering Ctte will be sponsors and PM. | 1. Loss of momentum without adequate governance 2. Unwilingness of partners to change processes 3. Complexity and regulatory requirements effecting manaufacturing process changes. | This forms the first phase of an ongoing leadtime reduction program. Results from the options workshop will be used in a series of phases.
There is nothing below this Line

## Worked Example Timeline
Schedule B3 Development Road Map | [8 empty] | WORKED EXAMPLE
This worked example is based on a supplier whose objective is to reduce their lead time by changing their manufacturing process. All the activities and products are fictitious and the example is provided only to show how to fill in the template
Page 2 TimeLine
Objective Name | Lead Time Reduction Project
| Section 3 | [20 empty] | 2015 | [40 empty] | 2016 | [16 empty] | 2017
| Activity Name | Forecast Duration in Weeks | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  | February | March | April |  | May |  | June | July |  | August | September | October |  | November | December | January |  | February | March | April |  | May |  | June | July |  | August | September | October |  | November | December
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
| Team Mobilisation and Kick Off | 2 | bar: January 4; February 7; February 9; March 11; March 13; April 17; June 23; June 25; August 33; August 35; September 37; September 39; October 43
| Internal Review and Mapping of Production Processes | 9 | bar: January 5 to April 15; April 17; June 23; June 25; August 33; August 35; September 37; September 39; October 43
| Identification of choke points in manufacturing process | 7 | bar: January 5; February 7; February 9 to April 17; June 23; June 25; August 33; August 35; September 37; September 39; October 43
\ | bar: January 5; February 7; February 9; March 11; March 13; April 17; June 23; June 25; August 33; August 35; September 37; September 39; October 43
| Analysis of supplier lead times and inventory policy | 11 | bar: January 5 to April 17; June 23; June 25; August 33; August 35; September 37; September 39; October 43
| Analysis of demand forecasts and provided lead times | 9 | April 18: 2
| Workshop Preparation | 3 | bar: January 5; February 7; February 9; March 11; March 13; April 17 to May 21; June 23; June 25; August 33; August 35; September 37; September 39; October 43
| Option Workshop Delivering Prioritised Outputs | 2 | May 22: 3
| Process Design for Priority Process Changes | 4 | June 26: 4
| Training and Process Changes Piloting | 4 | August 33: 5
| Full Roll Out Manufacturing Process Changes | 6 | bar: January 5; February 7; February 9; March 11; March 13; April 17; June 23; June 25; August 33 to September 39; October 43
| Roll out to demand management process changes | 6 | bar: January 5; February 7; February 9; March 11; March 13; April 17; June 23; June 25; August 33 to September 39; October 43
| Introduction of new stocking policy | 4 | bar: January 5; February 7; February 9; March 11; March 13; April 17; June 23; June 25; August 33; August 35; September 37; September 39 to October 43
| Final Review/Close out and Initiation of Phase 2 | 2 | November 45: 6
Project Management Steerco Meetings | bar: January 5; February 7; February 9; March 11; March 13 to April 15; April 17; June 23 to June 25; August 33; August 35 to September 37; September 39; October 43
| Phase 2 Roll Out |  | November 46: 7
|  |  | January 1: Q1 Milestones; April 14: Q2 Milestones; July 27: Q3 Milestones; October 40: Q4 Milestones | Q1 Milestones |  |  |  | Q2 Milestones |  |  |  |  | Q3 Milestones |  |  |  | Q4 Milestones |  |  |  | Q1 Milestones |  |  |  | Q2 Milestones |  |  |  |  | Q3 Milestones |  |  |  | Q4 Milestones
|  |  | January 1: Number; January 3: Milestone; April 14: Number; April 16: Milestone; July 27: Number; July 29: Milestone; October 40: Number; October 42: Milestone | Number | Milestone |  |  | Number | Milestone |  |  |  | Number | Milestone |  |  | Number | Milestone |  |  | Number | Milestone |  |  | Number | Milestone |  |  |  | Number | Milestone |  |  | Number | Milestone
|  |  | 1 |  | Team mobilised and work plans agreed | [10 empty] | 2 |  | Analysis Deliverable Complete | [10 empty] | 5 |  | Pilots complete lessons learnt implemented | [10 empty] | 6 |  | Close out meeting from Phase 1
[16 empty] | 3 |  | Prioritised roll out agreed, Detailed Planning Complete | [23 empty] | 7 |  | Phase 2 commences (Provisional)
[16 empty] | 4 |  | Training and roll out plans complete
Plant Shut Down for Electrical Upgade

## Objective 1 Background
Schedule B3 Development Road Map
Page 1 Background Information
Supplier Name |  | Initial Target
There is nothing this side of the line
Objective Name |  | Target Date
Benefit Sharing Proposal
| Initial Objective and Summarised Approach | Product Set Impacted | How Success(Value) is Measured
| Supplier Sponsorship and Resources Required | Actions Needed from the Global Fund | Actions Needed from Other Agencies
| Governance Model | Identified Risks | Proposal For Benefit Sharing
Additional Information Not Covered Above
There is Nothing Below This Line

## Objective 1 Timeline
Schedule B3 Development Road Map
Page 2 TimeLine
Opportunity Name | 0
[22 empty] | 2015 | [40 empty] | 2016 | [16 empty] | 2017
| Activity Name | Forecast Duration in Weeks | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  | February | March | April |  | May |  | June | July |  | August | September | October |  | November | December | January |  | February | March | April |  | May |  | June | July |  | August | September | October |  | November | December
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
\
|  |  | January 1: Q1 Milestones; April 14: Q2 Milestones; July 27: Q3 Milestones; October 40: Q4 Milestones | Q1 Milestones |  |  |  | Q2 Milestones |  |  |  |  | Q3 Milestones |  |  |  | Q4 Milestones |  |  |  | Q1 Milestones |  |  |  | Q2 Milestones |  |  |  |  | Q3 Milestones |  |  |  | Q4 Milestones
|  |  | January 1: Number; January 3: Milestone; April 14: Number; April 16: Milestone; July 27: Number; July 29: Milestone; October 40: Number; October 42: Milestone | Number | Milestone |  |  | Number | Milestone |  |  |  | Number | Milestone |  |  | Number | Milestone |  |  | Number | Milestone |  |  | Number | Milestone |  |  |  | Number | Milestone |  |  | Number | Milestone

## Ideas Page
Schedule B3 Development Road Map
Ideas Page
Please List any ideas in addition to your objectives and complete the boxes below (Cells will expand to fit your text)
| Idea Name | Outline of the concept including any information you think relevent including ease of attainment, timescale of project, when to do it, level of potential value